## Milestone Plan
Milestone | Timeline | Objective | Work to Complete | Expected Output | Completion Evidence | Key Dependency | Status
M0. System Architecture & Basic Model Planning | 01 Sep – 14 Sep 2026 | Finalize the overall system architecture and prepare the basic model plan. | Prepare system architecture/blueprint; define detection node, response node, sensor flow, communication flow and planned response mechanism; prepare a basic model concept for the first working prototype. | System architecture/blueprint and basic model plan. | Architecture diagram, basic model sketch/mock-up and project plan. | Project definition | Completed
M1. Basic Fire Detection & Automated Response | 15 Sep – 05 Oct 2026 | Establish the basic detection and first-response foundation. | Build the basic flame-detection setup; configure ESP1 detection logic; establish ESP1-to-ESP2 wireless communication; implement initial response activation using servo, relay, low-voltage pump, buzzer and LED; perform controlled testing. | Basic working fire detection and automated response model. | Detection test, wireless communication test, response activation test, photos/video and test notes. | M0 | Completed
M2. Multi-Sensor Integration | 06 Oct – 19 Oct 2026 | Combine multiple sensor inputs to improve fire-condition assessment. | Integrate flame, temperature/humidity and gas/smoke sensors; verify wiring and electrical compatibility; synchronize readings; check sensor ranges and stability. | Integrated multi-sensor sensing system. | Combined sensor readings, wiring diagram and integration test results. | M1 | Completed
M3. Real-Time Data Collection & Data Processing | 20 Oct – 02 Nov 2026 | Create a reliable dataset for analysis and AI/ML development. | Define experimental conditions; collect NORMAL, FIRE and FALSE_ALARM data; record timestamps and experiment metadata; validate data; prepare processed working copies while preserving raw data. | Structured and validated project dataset. | CSV/session files, validation results and data summary. | M2 | Planned
M4. Feature Engineering & Baseline Analysis | 03 Nov – 16 Nov 2026 | Convert raw sensor readings into useful indicators for intelligent decision making. | Establish normal environmental baseline; calculate rolling statistics, signal variance, rate of change/first derivative and deviation from baseline; study sensor-fusion patterns and prepare ML-ready features. | ML-ready feature dataset and baseline definition. | Feature table, plots/statistics and documented baseline definition. | M3 | Planned
M5. AI/ML Model Development & Evaluation | 17 Nov – 07 Dec 2026 | Develop and objectively evaluate the fire-risk classification model. | Prepare experiment/session-separated train/validation/test data; train candidate models; compare models; evaluate confusion matrix, precision, recall and F1; use ROC-AUC where applicable; select the best validated model. | Validated AI/ML model and evaluation report. | Trained model file, evaluation report, confusion matrix and performance metrics. | M4 | Planned
M6. Intelligent Direction Detection & Response | 08 Dec – 15 Dec 2026 | Use directional sensing to improve response targeting. | Use servo-mounted flame sensor for directional scanning; record detected angle; map the angle to the response servo; test response timing and communication timeout. | Direction-aware response mechanism. | Angle test table, controlled demonstration and timeout test. | M1 + M5 | Planned
M7. Mobile Application & Alert Integration | 16 Dec – 20 Dec 2026 | Provide user-facing monitoring and fire alerts. | Connect the application to the project decision output; display fire status and relevant readings; implement alert flow; test alert delivery and basic interface behavior. | Mobile monitoring and alert module. | Application screenshots, alert test record and demonstration. | M5 | Planned
M8. Final System Integration & Validation | 21 Dec – 31 Dec 2026 | Combine and validate the complete planned MVP. | Integrate detection, multi-sensor sensing, data/AI decision, directional response, application and alerts; run controlled test scenarios; record failures and fixes; document limitations; prepare final demonstration. | Integrated MVP and final validation package. | End-to-end test results, final architecture, demonstration evidence and report. | M1–M7 | Planned

## Timeline
Milestone | Start Date | End Date | Duration | Dependency | Main Focus
M0 | 01-Sep-2026 | 14-Sep-2026 | 2 weeks | Project definition | Architecture & basic model planning
M1 | 15-Sep-2026 | 05-Oct-2026 | 3 weeks | M0 | Basic detection + automated response
M2 | 06-Oct-2026 | 19-Oct-2026 | 2 weeks | M1 | Multi-sensor integration
M3 | 20-Oct-2026 | 02-Nov-2026 | 2 weeks | M2 | Real-time data + processing
M4 | 03-Nov-2026 | 16-Nov-2026 | 2 weeks | M3 | Features + baseline
M5 | 17-Nov-2026 | 07-Dec-2026 | 3 weeks | M4 | AI/ML development + evaluation
M6 | 08-Dec-2026 | 15-Dec-2026 | 1 week | M1 + M5 | Direction + intelligent response
M7 | 16-Dec-2026 | 20-Dec-2026 | 1 week | M5 | App + alerts
M8 | 21-Dec-2026 | 31-Dec-2026 | 1.5 weeks | M1–M7 | Final integration + validation

## Detailed Work Checklist
Milestone | Task / Work Item | Evidence / Result to Record
M0. System Architecture & Basic Model Planning | Prepare overall system architecture
M0. System Architecture & Basic Model Planning | Define detection and response nodes
M0. System Architecture & Basic Model Planning | Define sensor-to-controller data flow
M0. System Architecture & Basic Model Planning | Define ESP1→ESP2 communication flow
M0. System Architecture & Basic Model Planning | Define planned automated response mechanism
M0. System Architecture & Basic Model Planning | Prepare basic model/mock-up concept
M1. Basic Fire Detection & Automated Response | Test flame sensor
M1. Basic Fire Detection & Automated Response | Configure ESP1 detection logic
M1. Basic Fire Detection & Automated Response | Configure ESP2 response logic
M1. Basic Fire Detection & Automated Response | Establish ESP1→ESP2 wireless link
M1. Basic Fire Detection & Automated Response | Test response servo
M1. Basic Fire Detection & Automated Response | Test relay and low-voltage pump
M1. Basic Fire Detection & Automated Response | Test buzzer and LED
M1. Basic Fire Detection & Automated Response | Test safety timeout
M1. Basic Fire Detection & Automated Response | Record controlled detection-response demonstration
M2. Multi-Sensor Integration | Integrate temperature/humidity sensing
M2. Multi-Sensor Integration | Integrate gas/smoke sensing
M2. Multi-Sensor Integration | Verify electrical/ADC compatibility
M2. Multi-Sensor Integration | Synchronize sensor readings
M2. Multi-Sensor Integration | Check ranges and stability
M2. Multi-Sensor Integration | Record multi-sensor integration results
M3. Real-Time Data Collection & Data Processing | Define experiment conditions
M3. Real-Time Data Collection & Data Processing | Collect NORMAL samples
M3. Real-Time Data Collection & Data Processing | Collect FIRE samples
M3. Real-Time Data Collection & Data Processing | Collect FALSE_ALARM samples
M3. Real-Time Data Collection & Data Processing | Store timestamps and metadata
M3. Real-Time Data Collection & Data Processing | Validate CSV/schema
M3. Real-Time Data Collection & Data Processing | Check missing/invalid/duplicate records
M3. Real-Time Data Collection & Data Processing | Create processed working copy without changing raw data
M4. Feature Engineering & Baseline Analysis | Establish normal environmental baseline
M4. Feature Engineering & Baseline Analysis | Calculate rolling statistics
M4. Feature Engineering & Baseline Analysis | Calculate signal variance
M4. Feature Engineering & Baseline Analysis | Calculate first derivative/rate of change
M4. Feature Engineering & Baseline Analysis | Calculate deviation from baseline
M4. Feature Engineering & Baseline Analysis | Study combined sensor behavior
M4. Feature Engineering & Baseline Analysis | Prepare ML-ready feature table
M5. AI/ML Model Development & Evaluation | Create session-separated train/validation/test split
M5. AI/ML Model Development & Evaluation | Train candidate classification models
M5. AI/ML Model Development & Evaluation | Compare candidate models
M5. AI/ML Model Development & Evaluation | Generate confusion matrix
M5. AI/ML Model Development & Evaluation | Calculate precision, recall and F1
M5. AI/ML Model Development & Evaluation | Calculate ROC-AUC where applicable
M5. AI/ML Model Development & Evaluation | Select validated model
M5. AI/ML Model Development & Evaluation | Save model and evaluation report
M6. Intelligent Direction Detection & Response | Test servo scan angles
M6. Intelligent Direction Detection & Response | Record flame direction/angle
M6. Intelligent Direction Detection & Response | Map detected angle to response servo
M6. Intelligent Direction Detection & Response | Test response timing
M6. Intelligent Direction Detection & Response | Test communication-loss timeout
M6. Intelligent Direction Detection & Response | Document directional response results
M7. Mobile Application & Alert Integration | Connect application to decision output
M7. Mobile Application & Alert Integration | Display fire status
M7. Mobile Application & Alert Integration | Display relevant sensor readings
M7. Mobile Application & Alert Integration | Implement alert flow
M7. Mobile Application & Alert Integration | Test alert delivery
M7. Mobile Application & Alert Integration | Capture application evidence
M8. Final System Integration & Validation | Integrate all planned modules
M8. Final System Integration & Validation | Run normal-condition tests
M8. Final System Integration & Validation | Run controlled fire-condition tests
M8. Final System Integration & Validation | Run false-alarm scenarios
M8. Final System Integration & Validation | Record failures and fixes
M8. Final System Integration & Validation | Document limitations
M8. Final System Integration & Validation | Prepare final demonstration
M8. Final System Integration & Validation | Compile final validation evidence